## Sheet1
Task ID | Task Name | Owner | Start | End | Duration | Status | Dependency
1 | Project Initiation | Michael Chen | W1 | W1 | 3 days | Planned | —
2 | Requirement Gathering | Michael Chen | W1 | W2 | 7 days | Planned | 1
3 | BRD Review & Approval | Emma Richardson | W2 | W2 | 3 days | Planned | 2
4 | Wireframes | Sophia Martinez | W3 | W3 | 5 days | Planned | 3
5 | UI Design | Sophia Martinez | W3 | W4 | 10 days | Planned | 4
6 | Design Approval | Stakeholders | W4 | W4 | 2 days | Planned | 5
7 | Frontend Dev | Daniel Brooks | W5 | W8 | 20 days | Planned | 6
8 | Backend Dev | Aisha Khan | W5 | W8 | 20 days | Planned | 6
9 | Integration | Dev Team | W9 | W9 | 5 days | Planned | 7,8
10 | QA Testing | Ryan Patel | W10 | W11 | 10 days | Planned | 9
11 | UAT | Business Owner | W11 | W12 | 7 days | Planned | 10
12 | Deployment | James Wilson | W12 | W12 | 3 days | Planned | 11